## Agile Delivery Questionnaire
No. | Question | Category | Compliance Score | Remarks
1 | How will you structure sprints and deliverables to ensure the development of native iOS and Android apps is completed within the 12-18 month timeline? | Delivery Approach
2 | What mechanisms will you implement to gather real-time feedback from the IT Department and Operations Team during each sprint to ensure alignment with project goals? | Collaboration and Communication
3 | Can you provide a detailed plan for mitigating potential implementation delays, including specific strategies for addressing dependencies and bottlenecks? | Risk Management
4 | How will you ensure that the real-time flight status feature is developed with high reliability and accuracy, and what testing protocols will be applied to validate its performance? | Quality Assurance
5 | Describe the expertise of your team in developing mobile check-in and boarding pass features for airlines. How will you ensure these functionalities integrate seamlessly with existing airline systems? | Team Structure and Expertise
6 | What specific agile delivery practices will you use to ensure push notifications are implemented and tested early to gather user feedback from stakeholders such as the Operations Team? | Delivery Approach
7 | How will you address integration challenges with existing airline operations systems, and what tools or processes will you use to identify and resolve compatibility issues? | Risk Management
8 | What is your approach to ensuring offline capability is fully functional and tested across both iOS and Android platforms before deployment? | Quality Assurance
9 | How will you collaborate with the Executive Leadership team to ensure the project remains within budget and aligns with the strategic goals of the airline? | Collaboration and Communication
10 | What specific metrics and reporting formats will you use to provide progress updates to the IT Department and Executive Leadership throughout the 12-18 month timeline? | Progress Reporting
11 | How will you ensure that the final product drives user adoption among passengers and staff, and what methods will you use to measure adoption rates post-launch? | Success Criteria
12 | What is your approach to managing scope changes during the project, and how will you ensure that any changes do not impact the timeline or budget? | Change Management
13 | Describe how you will prioritize and deliver features such as real-time flight status and push notifications to provide early value to the Operations Team and passengers. | Delivery Approach
14 | What specific tools and communication channels will you use to facilitate collaboration between your development team and the IT Department throughout the project lifecycle? | Collaboration and Communication
15 | How will you ensure that your cost estimates remain accurate, and what steps will you take to prevent budget overruns during the 12-18 month implementation period? | Risk Management
16 | What testing methodologies will you use to ensure the mobile check-in and boarding pass features meet industry standards and provide a seamless user experience? | Quality Assurance
17 | Can you provide examples of past projects where you successfully delivered similar mobile app functionalities (e.g., offline capability or real-time updates) within a similar timeline and budget constraints? | Team Structure and Expertise
18 | How will you ensure that all stakeholders, including Operations Team and Executive Leadership, are involved in key decision-making processes throughout the project lifecycle? | Collaboration and Communication
19 | What contingency plans do you have in place to address potential delays caused by unforeseen technical challenges or external dependencies? | Risk Management
20 | How will you measure the success of the mobile app post-launch, and what KPIs will you use to demonstrate on-time delivery, budget adherence, and user adoption rates? | Success Criteria