## Agile Delivery Questionnaire
No. | Question | Category | Compliance Score | Remarks
1 | How will you structure your sprints and deliverables during the 6-month platform development phase to ensure timely completion of the mobile-first coordination platform while allowing feedback from ground handling teams and operations centers? | Delivery Approach
2 | What specific strategies will you use to ensure IoT sensors and wearable devices are fully integrated within the 2-month hardware integration phase, and how will you collaborate with the IT departments at the airports during this process? | Hardware Integration
3 | How will you ensure API integration with fueling and catering systems is completed without delays during the platform development phase, and how will you address potential compatibility issues with existing systems? | Risk Management
4 | What steps will you take to deploy the pilot rollout at two airports within the 9–10-month timeline, and how will you gather and incorporate feedback from ground handling teams and airline executives during this phase? | Pilot Rollout
5 | How will you ensure the full network rollout across 15+ airports is completed within the 11–12-month timeline, and what contingency plans do you have in place to address potential delays or unforeseen issues? | Full Rollout
6 | How will your machine learning delay prediction models be trained and validated to ensure they contribute to a 12-point improvement in on-time performance and a 30% reduction in ground delay minutes? | Machine Learning Models
7 | What communication and collaboration methods will you use to ensure real-time coordination among ground handling teams, operations centers, and airport management during the rollout phases? | Stakeholder Collaboration
8 | What measures will you take to manage resistance to change among ground handling teams and ensure high adoption rates of the platform and wearables? | Change Management
9 | How will you ensure that the platform’s real-time communication and task tracking features are optimized to achieve a 5-minute reduction in average turnaround time? | Performance Optimization
10 | What processes will you use to report progress to stakeholders, including airline executives and airport management, and how often will these reports be shared during each project phase? | Progress Reporting
11 | What specific quality assurance measures will you implement during the development and rollout phases to ensure the platform meets the success criteria and delivers positive ROI within 9 months of deployment? | Quality Assurance
12 | How will you structure your team to ensure expertise in mobile-first platform development, IoT integration, and machine learning, and what roles will be dedicated to stakeholder engagement and risk management? | Team Structure
13 | What contingency plans will you implement to manage potential cost overruns during the hardware integration and rollout phases, and how will you ensure the project stays within the $2.9M budget? | Risk Management
14 | How will you ensure seamless integration of IoT sensors and wearables with the real-time communication platform, and what testing protocols will you use to validate their performance in live airport environments? | IoT Integration
15 | What approach will you use to ensure the platform’s API integrations with fueling and catering systems are capable of handling real-time updates without causing delays or errors during high-traffic periods? | API Integration
16 | How will you address stakeholder concerns about the platform’s ability to deliver measurable improvements in on-time performance and ground delay reduction, and what data will you present to support these claims during the pilot phase? | Stakeholder Communication
17 | What specific methodologies will you use to predict and mitigate risks of delayed development during the first 6 months, and how will you ensure alignment with the 12-month project timeline? | Risk Mitigation
18 | How will you gather and incorporate feedback from ground handling teams and operations centers during the pilot rollout to refine the platform before the full network deployment? | Feedback Integration
19 | What training programs or materials will you provide to ground handling teams and airport management to ensure smooth adoption of the platform and wearable devices during the rollout phases? | Change Management
20 | How will you validate the platform’s ability to achieve a 5-minute reduction in turnaround time and ensure these results are consistently replicated across all 15+ airports after full deployment? | Performance Validation